## Annex 5 FP SCA Malawi
Annex 5 | Implementation Timetable
Project Title | Climate resilient health and well being for rural communities in Southern Malawi
Accredited Entity | Save the Children Australia
Version | Version: Final B.40 - 20 September 2024
Activity | Description | Milestone or Deliverable | Deliverable Number | By what Quarter | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Outcome 1 | Reduced risk from climate-sensitive diseases and conditions
Output 1.1 | Climate-informed health surveillance and Early Warning Alert Response System (EWARS) | bar: Year 1 Q2 to Year 3 Q4
Activity 1.1.1 | Strengthen the climate-informed health surveillance system by identificatying alert triggers for climate-sensitive health conditions | 4 new thresholds and warning levels set for each of the climate-sensitive diseases/conditions | 1 | Q2 Year 2 | bar: Year 1 Q2 to Year 2 Q2
Activity 1.1.2 | Strengthen the institutional architecture for managing the ongoing operation of the climate-informed Early Warning and Response System (EWARS) | New Data Software for EWARS designed and installed in 5 sentinel sites to link climate and health data and automatically generate warnings | 2 | Q 2 Year 2 | Year 2 Q2: 2
|  | Dissemination workshop held with 120 government officials | 3 | Q 4Year 3 | Year 3 Q4: 3
|  | At least 60 government officials (national and district) trained in cascading EWARS from national to district and sub-district levels | 4 | Q2 Year 2 | Year 2 Q2: 4
|  | 75 officials in non-project districts trained on new EWARS system | 5 | Q4 Year 3 | Year 3 Q4: 5
|  | 1 National committee established to meet quarterly for monitoring and oversight | 6 | Q1 Year 2 | Year 1 Q2: 6
Activity 1.1.3 | Establish sentinel sites at selected healthcare facilities to provide improved climate and health data for the health Early Warning and Response System (EWARS) | 5 sentinel sites established chosen from target health facilities in project districts | 7 | Q1 Year 3 | Year 3 Q1: 7
Output 1.2 | District Health Adaptation Plans (DHAPs) | bar: Year 1 Q3 to Year 3 Q4
Activity 1.2.1 | Facilitate preparation and local endorsement of DHAPs in 6 project districts | 6 District Health Adaptation Plans produced and validated by the District Executive Committees (DEC) | 8 | Q2 Year 3 | Year 3 Q4: 8
|  | 150 district officials trained in implementing the DHAPs | 9 | Q4 Year 2 | Year 2 Q4: 9
|  | 1 toolkit for developing and implementing DHAPs produced and delivered in 22 non-project districts (600 copies) | 10 | Q4 Year 3 | Year 3 Q4: 10
Activity 1.2.2 | Advocate for stronger integration of climate-resilient health within adaptation planning at district and sub-district level | 6 coalition-building meetings held in target districts | 11 | Q1 year 3 | Year 2 Q3: 11
|  | Review of 6 district plans | 12 | Q1 year 3 | Year 3 Q1: 12
|  | 1 Advocacy strategy created and validated between multi-sectoral stakeholders | 13 | Q1 year 3 | Year 3 Q1: 13
Outcome 2 | Healthcare infrastructure is able to deliver service and care in the context of changing climate risk
Output 2.1 | Climate-resilient health centres, district hospitals and central hospitals and schools for community health | bar: Year 1 Q3 to Year 5 Q2
Activity 2.1.1 | Develop a national standard for climate-resilient healthcare facilities | 1 National standard created and validated by multi-sectoral stakeholders. | 14 | Q2 Year 2 | Year 2 Q2: 14
|  | 20 national-level officials trained on new national standard | 15 | Q3 year 2 | Year 2 Q3: 15
Activity 2.1.2 | Strengthen the climate-resilience of healthcare facilities | Solar installations implemented in 79 health facilities. | 16 | Q4 Year 4 | Year 4 Q4: 16
|  | Improved WASH facilities (e.g. Rainwater harvesting and solar pumps) installed in 79 health facilities | 17 | Q4 Year 4 | Year 4 Q4: 17
|  | New screening tool created and delivered to 22 non-project districts | 18 | Q1 Year 3 | Year 3 Q1: 18
|  | Maintenance committees established and trained for all 79 facilities | 19 | Q1 Year 3 | Year 3 Q1: 19
Activity 2.1.3 | Build capacity of Malawi’s health sector to apply the climate-resilient healthcare facility standard | 75 officials from non-project districts are trained on standard and take part in study visits to see model health facilities. | 20 | Q 2 Year 5 | Year 5 Q2: 20
Activity 2.1.4 | Develop guidelines for climate-resilient WASH facilities | Guideline for climate-resilient WASH developed and validated by key stakeholders | 21 | Q3 Year 2 | Year 2 Q3: 21
|  | 50 multi-sectoral officials trained on using new WASH guidelines | 22 | Q1 Year 3 | Year 3 Q1: 22
Activity 2.1.5 | Upgrade WASH facilities at schools to improve children's health under climate change | Improved WASH facilities installed in 400 schools | 23 | Q1 Year 5 | Year 5 Q1: 23
|  | Maintenance committees established and trained at all 400 schools | 24 | Q1 Year 5 | Year 5 Q2: 24
Outcome 3 | Healthcare staff are able to deliver service and care in the context of changing climate risk
Output 3.1 | Healthcare staff trained in managing climate-related disease monitoring, health messaging and disease treatment and prevention | bar: Year 1 Q2 to Year 5 Q2
Activity 3.1.1 | Build data collection capacity to strengthen surveillance of climate-related diseases | 25 district staff (District Health Office) trained on surveillance operation and data entry | 25 | Q1 Year 3 | Year 3 Q1: 25
|  | 90 Health Surveillance Assistants (HSAs) and Senior HSAs trained on surveillance operations and data entry | 26 | Q3 Year3 | Year 3 Q3: 26
Activity 3.1.2 | Build capacity among district and community healthcare staff on climate and health, and use of EWARS to disseminate early warnings to communities | Training module on climate-informed EWARS designed and endorsed by MoH | 27 | Q4 Year 2 | Year 2 Q4: 27
|  | National cadre of 25 trainers receive ‘training of trainers' and are equipped to deliver training to staff at district and sub-district level | 28 | Q2 Year 3 | Year 3 Q2: 28
|  | 650 HSAs and SHSAs trained in total (by national cadre) on implementing the EWARS across the 6 project districts and 79 health facilities | 29 | Q4 Year 3 | Year 3 Q4: 29
|  | 5,200 Community Healthcare Volunteers (CHV) trained in new EWARS mechanism across the 25 TAs | 30 | Q2 Year 5 | Year 5 Q2: 30
Activity 3.1.3 | Provide medical supplies and technologies for climate health risk reduction and response | 1 New climate-sensitive procurement method developed and validated by MoH and Ministry of Finance | 31 | Q1 Year2 | Year 2 Q1: 31
|  | Treatment for severe or moderate acute malnutrition delivered to 35,000 total children, and pregnant and lactating women | 32 | Q1 Year 5 | Year 5 Q1: 32
|  | 81,000 doses of cholera and diarrhoeal treatment delivered by HSAs | 33 | Q1 Year 5 | Year 5 Q1: 33
|  | Malaria nets and seasonal chemoprevention delivered to at least 75,000 households | 34 | Q1 Year 5 | Year 5 Q1: 34
Activity 3.1.4 | Equip healthcare workers with MHPSS capacity to address mental health impacts of changing climate | Training manual on MHPSS developed and endorsed by MoH | 35 | Q 3 Year 2 | Year 2 Q3: 35
|  | 1,000 HSAs and SHSAs trained on MHPSS services | 36 | Q4 Year 3 | Year 3 Q4: 36
Activity 3.1.5 | Build capacity among district and community healthcare staff to address the gendered impacts of a changing climate | 1 Training module on climate impacts on gender issues created and validated by MoH | 37 | Q3 Year 2 | Year 2 Q3: 37
|  | 2,000 district and community-level staff trained on gendered impacts of climate change | 38 | Q4 Year 3 | Year 3 Q4: 38
|  | Procurement method for GBV, SHRH and CEFM treatment supplies revised to incorporate climate impacts | 39 | Q4 Year 3 | Year 3 Q4: 39
Outcome 4 | Community level health is more resilient in the context of changing climate risk
Output 4.1 | Stronger community capacity to reduce health risks from climate change | bar: Year 1 Q2 to Year 5 Q2
Activity 4.1.1 | Equip community structures to provide knowledge and skills for climate-resilient WASH facilities to community members | 375 members of ACPCs trained on effective use of climate-resilient WASH facilities | 40 | Q2 Year 3 | Year 3 Q2: 40
|  | Women-led WASH monitoring groups established in at least 400 target communities | 41 | Q4 Year3 | Year 3 Q4: 41
Activity 4.1.2 | Embed understanding of early warnings and alert protocols within communities, including children | Early warning materials developed and delivered in 500 villages through mixed channels (e.g. leaflets, SMS, radio jingles) | 42 | Q2 Year 4 | Year 4 Q2: 42
|  | At least 5,000 out of school children, elderly people and people with disabilities receive early warning materials across the 500 target communities via mixed channels (e.g. radio, leaflets) | 43 | Q1 Year 5 | Year 5 Q1: 43
Activity 4.1.3 | Train communities to reduce their own vulnerability to climate-induced health risk | New community-level public health messaging to reduce risk of climate induced impact developed and validated by multi-sectoral stakeholders | 44 | Q4 Year 2 | Year 2 Q4: 44
|  | 2 mobile health units equipped and visits conducted across 500 villages to promote messaging on climate-induced health risks | 45 | Q2 Year 5 | Year 5 Q2: 45
|  | 3,375 traditional healers trained on climate-induced health risks | 46 | Q2 Year 5 | Year 5 Q2: 46
Activity 4.1.4 | Support families with pregnant and breastfeeding women and children under two to produce climate-resilient foods and provide quality complementary feeding to children under two | Integrated homestead farming starter kits delivered in 500 villages | 47 | Q2 Year 5 | Year 5 Q1: 47
|  | Community Health Action Groups (CHAGs) trained on nutritious feeding in 500 villages | 48 | Q4 Year 4 | Year 4 Q4: 48
|  | 35,000 households trained in homestead farming approach | 49 | Q2 Year 5 | Year 5 Q2: 49
|  | Nutrition starter kits (including seeds, organic fertiliser) delivered to at least 35,000 mothers across 500 villages across project lifecycle | 50 | Q3 Year 2 | Year 2 Q3: 50
Activity 4.1.5 | Strengthen communities’ capacities to reduce their vulnerability to the health impacts of climate change, particularly gendered impacts | GESI-focused community groups established or strengthened in 200 villages | 51 | Q4 Year 2 | Year 2 Q4: 51
|  | Clear action plan created for each of 200 groups | 52 | Q1 Year 3 | Year 3 Q1: 52
|  | 10,000 women, girls, men and boys trained on gendered impacts of climate change | 53 | Q4 Year 4 | Year 4 Q4: 53
Component 5 | Monitoring, Evaluation, Accountability and Learning
Activity 5.1.1 | Analyse data to inform the project, and conduct routine monitoring to ensure progress by all partners | Inception report published | 54 | Q3 Year 1 | Year 1 Q3: 54
|  | APR submitted | 55 | Q2 Year 5 | Year 2 Q1: 55; Year 3 Q1: 55; Year 4 Q1: 55; Year 5 Q1: 55; Year 6 Q1: 55
|  | Final project review and close out held | 56 | Q4 Year 5 | Year 5 Q4: 56
Activity 5.1.2 | Conduct baseline, mid-term and endline assessments to evaluate and ensure sustainable progress | Baseline report published | 57 | Q4 Year 1 | Year 1 Q4: 57
|  | Midterm report published | 58 | Q1 Year 4 | Year 4 Q1: 58
|  | Endline report published | 59 | Q4 Year 5 | Year 6 Q2: 59