## Annex 5
Component | sub-component Title | Output Title | Activity | Activity Title | Lead Financer | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2 Q1 | Y2 Q2 | Y2 Q3 | Y2 Q4 | Y3 Q1 | Y3 Q2 | Y3 Q3 | Y3 Q4 | Y4 Q1 | Y4 Q2 | Y4 Q3 | Y4 Q4 | Y5 Q1 | Y5 Q2 | Y5 Q3 | Y5 Q4 | Y6 Q1 | Y6 Q2 | Y6 Q3 | Y6 Q4
Component 1 | Sub-Component 1.1: Investments in irrigation canals upgrading | Output 1.1.1: Open canals shifted from to closed systems benefiting 8,457 people | Activity 1.1.1.1 | Engineering design | GCF |  |  | 1 | Engineering design completed
|  |  | Activity 1.1.1.2 | Construction supervision | GCF |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Activity 1.1.1.3 | Construction works | GCF | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 68 km of canals rehabilitated
|  |  | Activity 1.1.1.4 | Operation & maintenance of Works | Government | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Activity 1.1.1.5 | Technical coordination & oversight | GCF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sub-Component 1.2: Investments in Renewable Energy Systems | Output 1.2.1: One km of Water canals covered with solar panels, providing 1,000 kW of renewable energy | Activity 1.2.1.1 | Engineering design | FAO |  |  | 1 | Engineering design completed
|  |  | Activity 1.2.1.2 | Construction supervision | FAO |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Activity 1.2.1.3 | Installation of Solar Systems | FAO |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 MWp of solar systems installed
|  |  | Activity 1.2.1.4 | Operation & maintenance | FAO | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sub-Component 1.3: Investments in knowledge transfer, behaviour change and training | Output 1.3.1: 500 technical staff trained in design, installation and maintenance of irrigation, drainage and energy technologies | Activity 1.3.1.1 | Capacity development of technical staff | GCF | [16 empty] | 1 | 500 technicians trained
|  |  | Activity 1.3.1.2 | Update Vocational School´s and technical institutes curricula | GCF | [12 empty] | 1 | 1 | 1 | Curricula updated
|  | Output 1.3.2: 15 WUAs supported in developing and adopting more efficient and climate sensitive water-distribution plans. | Activity 1.3.2.1 | Establish and Support WUAs in the selected project areas | Government |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Activity 1.3.2.2 | Reinforce WUA members’ technical and managerial capabilities | GCF | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 15 WUAs are established and have their capacity reinforced
Component 2 | Sub-Component 2.1: Strengthening Adaptive Capacity of Farmers | Output 2.1.1: 400 Extension Staff trained on climate resilient agricultural practices and technologies | Activity 2.1.1.1 | Technical coordination and oversight | GCF | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Activity 2.1.1.2 | Develop the training curricula to support the adoption of CRA | FAO |  |  | 1 | 1
|  |  | Activity 2.1.1.3 | Train the master trainers | FAO |  |  | 1 | 12 Master Trainers trained
|  |  | Activity 2.1.1.4 | Conduct the training of the extension service staff | FAO |  |  | 1 | 400 extensionists trained
|  | Output 2.1.2: Enhanced capacity of 10 000 farmers in Climate Resilient Agriculture | Activity 2.1.2.1 | Set-up the farmer field schools for training local farmers | GCF |  |  |  | 1 | 1
|  |  | Activity 2.1.2.2 | Set up 400 project demonstration farms or plots to validate the benefits of the selected CRA practices and technologies | GCF | [8 empty] | 1 | 1 | 1 | 1 |  | 400 project demonstration farms set up | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Output 2.1.3: 100,000 farmers reached through ICT4CC technologies | Activity 2.1.3.1 | Enhance awareness of climate resilient agricultural practices through ICT | FAO |  |  |  |  | 1 | 1 | 1 | ICT4CC action plan developed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sub – Component 2.2. Enhancing Awareness about Renewable Energy Applications for agriculture | Output 2.2.1: Technical Capacities of 90 stakeholders and knowledge of 12,000 citizens on solar energy increased through trainings and awareness raising events | Activity 2.2.1.1 | Enhance Technical Capacities of extensionists and other stakeholders on Solar energy for agriculture | FAO |  |  | 1 | 1 | 1 | 1 | 1 |  | 3 solar training events organized | 1 | 1 | 1 | 1 | 1 | 1 | 3 solar training events organized
|  |  | Activity 2.2.1.2 | Increase awareness of the population on the advantages and opportunities of solar energy | FAO |  |  | 1 | 1 | 1 | 3 open energy days organized | 1 | 1 | 1 | 3 open energy days organized | 1 | 1 | 1 | 3 open energy days organized | 1 | 1 | 1 | 3 open energy days organized | 1 | 1 | 1 | 1 | 1 | 1
| Sub-Component 2.3: Enhancing Climate Resilience for Women | Output 2.3.1 : A cadre of Climate Wise Women (CWW) trained as change agents for climate adaptation | Activity 2.3.1.1 | Technical Assistance for Climate Wise Women (CWW) sub-component | FAO | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Activity 2.3.1.2 | Develop Social and Behavior Change Communication Strategy for CWW | FAO |  |  |  |  | 1 | 1
|  |  | Activity 2.3.1.3 | Designing Training Modules for Master Trainers and Climate Wise Women | FAO | [5 empty] | 1 | 1
|  |  | Activity 2.3.1.4 | Provide Training to Master Trainers | FAO | [6 empty] | 1 | 1
|  |  | Activity 2.3.1.5 | Select and train CWW | FAO | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 150 CWW trained
|  | Output 2.3.2. 40,500 Women adopt for climate adaptive measures. | Activity 2.3.2.1 | Dissemination of climate resilient practices by CWW | GCF | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Activity 2.3.2.2 | Organizing multi-stakeholder Climate Wise Women Forums | FAO | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Climate Wise Women Forum | 1 | 1 | Climate Wise Women Forum |  |  | Climate Wise Women Forum
Component 3 | Sub-Component 3.1 Promotion of agriculture water policies and planning | Output 3.1.1: A climate resilient water allocation strategy and its action/legal/coordination plan developed | Activity 3.1.1.1 | Conduct multi-stakeholder consultation meetings | GCF |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | draft climate resilient water allocation strategy developed | 1 | 1 | 1 | 1 | climate resilient water allocation strategy validated | climate resilient water allocation strategy developed | 1 | 1 | 1 | 1
|  | Output 3.1.2: Improved national compliance practices for management of irrigation water supply | Activity 3.1.2.1 | Analyse national compliance practices and the monitoring capacity | FAO | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Action plan for new service delivery developed
|  |  | Activity 3.1.2.2 | Conduct knowledge exchange processes | FAO | [11 empty] | 1 | 1 | Webinar | 1 | Webinar | 1 | study visit | Webinar | 1 | study visit | Webinar | 1 | 1
| Sub-Component 3.2. Support to solar energy policies implementation | Output 3.2.1: Enhanced planning for solar rural electrification | Activity 3.2.1.1 | Develop an action plan for solar rural electrification | FAO |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | Solar Road map developed |  |  |  |  | 1 | 1 | 1 | 1
Project Monitoring and Evaluation |  |  |  |  | GCF | Baseline | 1 | 1 | Annual Report | 1 | 1 | 1 | Annual Report | 1 | 1 | 1 | Annual Report | Mid-term evaluation | 1 | 1 | Annual Report | 1 | 1 | 1 | Annual Report | 1 | 1 | Terminal Evaluation | Annual Report